**Draft Plan of Action of the SOP on Law Enforcement Cooperation between Thailand and Cambodia**

**2022 – 2024**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Sub-Objectives** | **Activities** | **Responsible agency** | **Duration (years)** | | | **Expected result**  **will receive** |
| **2022** | **2023** | **2024** |  |
|  | Central Cooperation Center  (Annex 1) | 1.1 Draft and Finalize Annex 1 on role and responsibility of central cooperation center | Cambodia:  Thailand: |  |  |  | Annex 1 completed |
|  |  | 1.2 Assign relevant parties as central cooperation center | Cambodia:  Thailand: |  |  |  | Central cooperation center was established. |
|  | Competence Officials  (Article 3 of SOP) | 1.1 Draft and Finalize Role and Responsibility of Competence Officials |  |  |  |  | Annex 2 of SOP completed |
| 1.1 Draft and Finalize Victim Screening Form |  |  |  |  |  |
| 1.2 Identification Form including Informed Consent Form, Risk Assessment Form… |  |  |  |  |  |
|  | Victim Identification  (Article 4 of SOP) | 1.1 Draft and Finalize Victim Screening Form, Identification Form, Informed Consent Form, Risk Assessment Form |  |  |  |  | Annex 3 of SOP completed |
|  | 1.2 Guideline in Identifying Presumed and/or Victim of Trafficking |  |  |  |  |  |
|  | Criminal Procedure  (Article 5) | 1.1 Guideline in Providing Protection Services to Victims of Trafficking during legal process.   * Investigation * Court hearing * Compensation |  |  |  |  |  |
|  | Investigation and Information Sharing  (Article 6) | * 1. Draft and Finalize data sharing form, data protection agreement, procedure (flowchart for data sharing) |  |  |  |  |  |
| 1.2 Guideline for join investigation in accordance with the MoU on Bilateral Cooperation for Eliminating Trafficking in Persons and Protecting Victims of Trafficking 2014 and International/Regional Framework on TIP |  |  |  |  |  |
| 1.3 Draft Guideline for Law Enforcement Cooperation Meeting |  |  |  |  |  |
|  | International Cooperation | 1.1 Conduct bilateral training on cross border investigation |  |  |  |  |  |
|  |  | 1.2 Conduct study to map opportunity and challenges in implementing international cooperation on TIP between Cambodia and Thailand |  |  |  |  |  |